## Tabelle1
Checklist | Subcategory | Transparency | Alignment | Team Spirit | Clarity of Vision | Execution Focus
Delivering working, tested software every 4 weeks or less |  | 1 | 1 | 1 | 1 | 1
Delivering what the business needs most |  | 1 | 1 | 1 | 1 | 1
Process is continuously improving |  | 1 | 1 | 1 | 1 | 1
Retrospective happens after every sprint |  | 1 |  | 1
Results in concrete improvement proposals | x | 1 |  | 1
Some proposals actually get implemented | x | 1 |  | 1
Whole team + PO participates | x | 1 |  | 1 | 1
There is a product backlog (PBL) |  | 1 | 1 |  | 1 | 1
Top items are prioritized by business value | x |  | 1 |  | 1 | 1
Top items are estimated | x | 1 | 1 |  | 1
Estimates written by the whole team | x | 1 | 1 | 1 | 1
Top items in PBL small enough to fit in a sprint | x | 1 | 1 |  |  | 1
PO understands purpose of all backlog items | x | 1 | 1 |  | 1 | 1
Have sprint planning meetings |  | 1 | 1 | 1 | 1 | 1
PO participates | x | 1 | 1 | 1 | 1 | 1
PO brings up-to-date PBL | x | 1 | 1 |  | 1 | 1
Whole team participates | x | 1 | 1 | 1 | 1 | 1
Results in a sprint plan | x | 1 | 1 | 1 |  | 1
Whole team believes plan is achievable | x | 1 | 1 | 1
PO satisfied with priorities | x |  | 1 | 1 | 1 | 1
Timeboxed iterations | [5 empty] | 1
Iteration length 4 weeks or less | x | 1 | 1 | 1 |  | 1
Always end on time | x | 1 | 1 | 1 |  | 1
Team not disrupted or controlled by outsiders | x |  | 1 | 1 |  | 1
Team usually delivers what they committed to | x | 1 | 1 | 1 | 1 | 1
Team members sit together |  | 1 |  | 1
Max 9 people per team | x |  | 1 | 1
Clearly defined product owner (PO) |  | 1 | 1 |  | 1 | 1
PO is empowered to prioritize | x | 1 | 1 |  | 1 | 1
PO has knowledge to prioritize | x | 1 | 1 |  | 1 | 1
PO has direct contact with team | x | 1 | 1 | 1 | 1
PO has direct contact with stakeholders | x | 1 | 1 |  | 1
PO statements are consistent | x | 1 | 1 |  | 1
Team has a sprint backlog |  | 1 | 1 | 1 |  | 1
Highly visible | x | 1 | 1 |  |  | 1
Updated daily | x | 1 |  | 1 |  | 1
Owned exclusively by the team | x | 1 |  | 1 |  | 1
Daily Scrum happens |  | 1 | 1 | 1 |  | 1
Whole team participates | x | 1 |  | 1
Problems and impediments are surfaced | x | 1 | 1 | 1 |  | 1
Demo happens after every sprint |  | 1 | 1 |  | 1 | 1
Shows working, tested software that meets DoD | x | 1 | 1 | 1 | 1 | 1
Feedback received from stakeholders & PO | x | 1 | 1 | 1 | 1 | 1
Feedback effects PBL | x | 1 | 1 |  | 1
Have Definition of Done (DoD) |  | 1 |  | 1 |  | 1
DoD achievable within each iteration | x | 1 |  | 1 |  | 1
Team respects DoD | x | 1 | 1 | 1
Team has all skills needed to bring backlog items to Done |  |  | 1 | 1 |  | 1
Team members not locked into specific roles |  | 1 | 1 | 1 |  | 1
PBL and product vision is highly visible |  | 1 |  |  | 1
PO available when team is estimating |  | 1 | 1 | 1 | 1
Whole team knows top 1-3 impediments |  | 1 | 1 | 1 |  | 1
Team has strategy for how to fix top impediment | x |  |  | 1 |  | 1
Problem is in the hands of those who can solve it | x |  | 1 | 1 |  | 1
Team has a Scrum Master (SM) |  |  |  | 1
SM knows the team well | x |  |  | 1
All items in sprint plan are workable | x | 1 | 1 |  |  | 1
Team has a sprint burndown chart |  | 1
Highly visible | x | 1
Updated daily | x |  |  | 1
Daily Scrum is every day, same time & place |  | 1 | 1 | 1 |  | 1
PO participates at least a few times per week | x | 1 | 1 | 1
Max 15 minutes | x |  |  |  |  | 1
Each team member knows what the others are doing | x | 1 |  | 1 |  | 1
Having fun! High energy level. |  |  |  | 1
Discussing, criticizing, and experimenting with the process |  | 1 |  | 1